## Gantt Chart
PROJECT TITLE |  | LifeTrack
DATE |  | 2020-04-20
WBS Number | TASK TITLE | Duration | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12 |  |  |  |  | WEEK 13 |  |  |  |  | WEEK 14 |  |  |  |  | WEEK 15 |  |  |  |  | WEEK 16 |  |  |  |  | WEEK 17 |  |  |  |  | WEEK 18 |  |  |  |  | WEEK 19 |  |  |  |  | WEEK 20
|  |  | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Planning
1.1 | Scope and Goal Setting | 4 | bar: WEEK 1 M to WEEK 1 R
1.2 | Cost, Effort and Pricing Estimations | 2 | bar: WEEK 1 F to WEEK 2 M
1.3 | Budget | 2 | bar: WEEK 2 T to WEEK 2 W
2 | Designing
2.1 | Design System | 5 | bar: WEEK 2 R to WEEK 3 W
2.2 | Desing Database | 5 | bar: WEEK 3 R to WEEK 4 W
2.3 | Design software | 5 | bar: WEEK 4 R to WEEK 5 W
2.4 | Design Interface | 5 | bar: WEEK 5 R to WEEK 6 W
2.5 | Design specifications | 5 | bar: WEEK 6 R to WEEK 7 W
3 | Implementation and Testing
3.1 | Implementing the system | 35 | bar: WEEK 7 R to WEEK 14 W
3.2 | Implementing testing applications | 9 | bar: WEEK 14 R to WEEK 16 T
3.3 | Testing the system | 9 | bar: WEEK 16 W to WEEK 18 M
3.4 | Fixing bugs | 9 | bar: WEEK 18 T to WEEK 19 F
4 | Deployment and Maintenance
4.1 | Monitoring | 3 | bar: WEEK 20 M to WEEK 20 W
4.2 | Maintaining | 2 | bar: WEEK 20 R to WEEK 20 F